## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Edu Planner (Cloud Based) |  |  |  |  | ORGANIZATION NAME |  |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  |  | 2023-09-10
Group Leader | Jacy Lin | [5 empty] | Legend
Group Members | Daniel Amoruso, Angel Flores, Ramses Terry, Max Zedlovich
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/4/2023 |  | W2 9/11/2023 |  | W3 9/18/2023 |  | W4 9/25/2023 |  | W5 10/2/2023 |  | W6 10/9/2023 |  | W7 10/16/2023 |  | W8 10/23/2023 |  | W9 10/30/2023 |  | W10 11/06/2023 |  | W11 11/13/2023 |  | W12 11/20/2023 |  | W13 11/27/2023 |  | W14 12/4/2023
1 | Project Conception and Initiation | [6 empty] | First Week |  | Setting Up |  | Designing |  | Database Setup |  | Login Page |  | Sign-Up Page |  | Calendar Page |  | Calendar Page |  | Classes Page |  | Classes Page |  | Faculty List |  | Faculty List |  | Profile Page |  | Profile Page
1.1 | Setting up Github | Jacy | 2023-08-28 | 2023-09-04 | 6
1.1.1 | Setting up Webex Account | Jacy | 2023-08-28 | 2023-09-04 | 6
1.2 | Setting up XAMPP / Unreal Engine | Everyone | 2023-08-28 | 2023-09-04 | 6
1.3 | Setting up Discord | Jacy | 2023-09-04 | 2023-09-06 | 2
1.4 | Assigning Group Leader | Everyone | 2023-08-28 | 2023-09-04 | 6
1.5 | File/Folder Structuring | Jacy | 2023-09-13 | 2023-09-20 | 7
1.5 | SSH Access/Web Servers | Jacy | 2023-09-13 | 2023-09-20 | 7
2 | Design
2.1 | Create a Template | Jacy | 2023-09-11 | 2023-09-18 | 7
2.2 | Use Case Diagram | Jacy | 2023-09-18 | 2023-09-25 | 7
2.3 | Create a Sample Flowchart | Jacy | 2023-09-18 | 2023-09-25 | 7
2.3.1 | Data Base Schema Design | Angel | 2023-09-11 | 2023-09-18 | 7
2.4 | Ask school for Data Permission | Daniel | 2023-09-13 | 2023-09-20 | 7
2.5 | Design an overall flowchart | Daniel | 2023-09-20 | 2023-09-27 | 7
2.6 | SQL Diagram - Login Page | Daniel | 2023-10-04 | 2023-10-11 | 7
2.7 | SQL Diagram - Sign Up Page | Daniel | 2023-10-11 | 2023-10-18 | 7
2.8 | SQL Diagram - Calendar Page | Daniel | 2023-10-18 | 2023-11-01 | 14
2.9 | SQL Diagram - Classes Page | Daniel | 2023-11-01 | 2023-11-15 | 14
2.1 | SQL Diagram - Faculty Page | Daniel | 2023-11-15 | 2023-11-29 | 14
2.6 | Flowchart - Login Page | Jacy | 2023-10-04 | 2023-10-11 | 7
2.7 | Flowchart - Sign Up Page | Jacy | 2023-10-11 | 2023-10-18 | 7
2.8 | Flowchart - Calendar Page | Jacy | 2023-10-18 | 2023-11-01 | 14
2.9 | Flowchart - Classes Page | Jacy | 2023-11-01 | 2023-11-15 | 14
2.1 | Flowchart - Faculty Page | Jacy | 2023-11-15 | 2023-11-29 | 14
3 | Coding and Assembly
3.1 | HTML - Landing Page | Ramses | 2023-09-20 | 2023-09-27 | 7
3.1.2 | HTML - Navigation Bar | Ramses | 2023-10-04 | 2023-10-11 | 7
3.2 | HTML - Login Page | Jacy | 2023-10-04 | 2023-10-11 | 7
3.2.1 | HTML - Sign Up Page | Ramses | 2023-10-11 | 2023-10-18 | 7
3.3 | HTML - About Page | Daniel | 2023-10-18 | 2023-11-01 | 14
3.5 | HTML - Calendar Page | Ramses | 2023-11-01 | 2023-11-15 | 14
3.6 | HTML - Classes Page | Ramses | 2023-11-15 | 2023-11-29 | 14
3.7 | HTML - Faculty Page | Ramses | 2023-11-01 | 2023-11-15 | 14
3.8 | HTML - Admin Page | Ramses | 2023-11-15 | 2023-11-29 | 14
3.9 | HTML - Footer | Jacy | 2023-10-11 | 2023-10-18 | 7
3.1 | CSS - Landing Page | Max/Ramses | 2023-09-20 | 2023-09-27 | 7
3.1.2 | CSS - Navigation Bar | Max/Ramses | 2023-10-04 | 2023-10-11 | 7
3.2 | CSS - Login Page | Max/Jacy | 2023-10-04 | 2023-10-11 | 7
3.2.1 | CSS - Sign Up Page | Ramses | 2023-10-11 | 2023-10-18 | 7
3.3 | CSS - About Page | Daniel | 2023-10-18 | 2023-11-01 | 14
3.5 | CSS - Calendar Page | Ramses | 2023-11-01 | 2023-11-15 | 14
3.6 | CSS - Classes Page | Ramses | 2023-11-15 | 2023-11-29 | 14
3.7 | CSS - Faculty Page | Ramses | 2023-11-01 | 2023-11-15 | 14
3.8 | CSS - Admin Page | Jacy | 2023-11-15 | 2023-11-29 | 14
3.9 | CSS - Footer | Jacy | 2023-10-11 | 2023-10-18 | 7
4 | Data Management
4.1 | Generate Data Base (PHP) | Angel | 2023-09-27 | 2023-10-04 | 7
4.2 | Login Page | Angel | 2023-10-04 | 2023-10-11 | 7
4.2.1 | Sign Up Page | Angel | 2023-10-11 | 2023-10-18 | 7
4.2.2 | Calendar Page | Angel | 2023-10-18 | 2023-11-01 | 14
4.3 | Classes Page | Angel | 2023-11-01 | 2023-11-15 | 14
4.3.1 | Faculty List | Angel | 2023-11-15 | 2023-11-29 | 14
4.4 | Profile Page | Angel | 2023-11-29 | 2023-12-13 | 14
5 | Maintanence - Ensure Page Works
5.1 | Github - Login Page Maintanence | Max/Jacy | 2023-10-04 | 2023-10-11 | 7
5.2 | Github - Sign Page Maintanence | Max/Jacy | 2023-10-11 | 2023-10-18 | 7
5.2.1 | Github - Calendar Page Maintanence | Max/Jacy | 2023-10-18 | 2023-11-01 | 14
5.2.2 | Github - Classes Page Maintanence | Max/Jacy | 2023-11-01 | 2023-11-15 | 14
5.3 | Github - Faculty Page Maintanence | Max/Jacy | 2023-11-15 | 2023-11-29 | 14
5.3.1 | ADA Compliance Checking | Max | 2023-10-18 | 2023-11-01 | 14
5.4 | Consistency Fixes | Max | 2023-11-01 | 2023-11-15 | 14
5.5 | Responsiveness Fixes | Max | 2023-11-15 | 2023-11-29 | 14